## Sheet1
Projects in Execution | Public Entity's Name | Contractor/ Service Provider | Contractor/ Service Provider Nationality | Commencement (Contract Signing Date/site handover) | Duration in days | Envisaged completion | Revised Completion | Total Budget / Contract Value in N$ | Time Lapse in days | Expected completion Percentage | Average completion Percentage | Procurement Category | Number of people employed by the project | Last site visits | Comments | Project Status | Actual Cost to Date (Mil)
RA/SE-NAT 01-2016 Bureau services for the supply and Personalization of Driving License cards | Roads Authority | Business Connexion Namibia (Pty) Ltd JV 2identity | Namibian | Mar-19 | 2922 | Mar-27 |  | 111083076.62 | 2132 | 0.73 | 0.73 | Non-Consultancy Services | 15 |  | The Project design phase has been fully implemented and the project was handed over into operational and maintenance mode in March 2024 for the 3 year period. | In Progress | 53.69
W/RB/CPBN-04/2018: Upgrading of Okakarara VTC | NamibiaTraining Authority | Octagon Construction | Namibian | Apr-19 | 1194 | Apr-21 | Jul-22 | 64251259.24 | 2078 | 1.74 | 0.9 | Works | 81 | 11-Dec-24 | Contractor resumed on site in April 2024 with the expected completion date is end of October 2024, as per the approved programme of Works by the PA. Much of the work that has been done on site from April to August 2024 is remedial works repairing the demages that were caused by the wind and rain during the standstill period as well as correcting the defects. Thus why the physical progress remained 90% . | In Progress | 48.99
NCS/ONB/CPBN-02/2018: Procurement of Government Diamond Valuators | Ministry of Mines & Energy | Gem Diamond Namibia (Pty) Ltd | Namibian | Sept-19 | 2014 | Aug-24 | Mar-25 | 480000000 | 1948 | 0.97 | 0.97 | Non-Consultancy Services |  |  | Contract extended for 6 months from 01 Sept 2024 to 28 Feb 2025 | In Progress | 332.04
RA/CS-ICT/02-2016: Provision of Multiprotocol Label Switching (MPLS) and Internet Services to Roads Authority | Roads Authority | Data Dimension Pty | Namibian | Nov-19 | 1826 | Nov-24 |  | 21545005.61 | 1878 | 1.03 | 1 | Non-Consultancy Services |  |  | contract expired 10 November 2024 and no renewal.RA to conitue monitor,support and maintail all the network link. | In Progress | 21.54
G/OIB/CPBN-01/2019: Procurement of Design, Manufacturing, Testing and Delivery of Two Mobile Substations | Nampower | ABB South Africa (PTY) LTD | South African | Jan-20 | 1731 | Jul-21 | Oct-24 | 47282748.7 | 1807 | 1.04 | 0.97 | Goods |  |  | Fire incident at the factory on the 07 March 2021 impacted both mobile substations. Nampower rejected both Transformers and instructed ABB to procure from a diferent factory The re-design of both transformers are completed . The completion date has been udated inline with the extension of time request received from ABB. The manufacturing and testing of both transformer were completed and transformers are delivered to project assemle site on 21 June 2024.The transformers and accompaning equipments have been delivered to site and successfully installed in November 2024. | In Progress | 1400
W/ONB/CPBN-07/2019:Constrcution of Kunene VTC | NamibiaTraining Authority | Adaptive Building and Land Construction CC | Namibian | Sept-20 | 992 | Sept-22 | May-23 | 42795107.38 | 1572 | 1.58 | 1 | Works | 115 | 20-Mar-23 | The project is practically completed by 24 Nov 2023, and on Defect liability period for 12 months. The project was inagurated by the head of State on 07 August 2024 | In Progress | 39.46
NCS/ONB/CPBN-03/2019: The Provision of Cleaning Services to The Namibia University of Science and Technology | Namibia University of Science and Technology (NUST) | Adaptic Investment CC | Namibian | Nov-20 | 1641 | Oct-23 | Apr-25 | 12551341.5 | 1521 | 0.93 | 0.93 | Non-Consultancy Services | 45 | 20-Jun-23 | The intial contract period lapsed 31 October 2023. The Board approved six (6) months extension s as follows 1. from 01 November 2023- 30 April 2024. 2. from 01 May to 31 October 2024 3. From 01 Nov 2024 to 28 Feb 2025. | In Progress | 10.93
NCS/ONB/CPBN-03/2019: The Provision of Cleaning Services to The Namibia University of Science and Technology | Namibia University of Science and Technology (NUST) | LYPA Investment CC | Namibian | Nov-20 | 1641 | Oct-23 | Apr-25 | 15428921.8 | 1521 | 0.93 | 0.93 | Non-Consultancy Services | 50 | 20-Jun-23 | The intial contract period lapsed 31 October 2023. The Board approved six (6) months extension s as follows 1. from 01 November 2023- 30 April 2024. 2. from 01 May to 31 October 2024 3. From 01 Nov 2024 to 28 Feb 2025. | In Progress | 13.33
W/OIB/CPBN-06/2019: Reconstruction of canal section between Mahenene Border post and Olushandja Dam: Part A (Olushandja Section) | NamWater | Radial Truss Industries Ltd JV Imperative Construction & Engineering CC | Namibian | Feb-21 | 631 | Nov-22 | Feb-23 | 41575067.49 | 1412 | 2.24 | 0.97 | Works |  | 18-Oct-23 | The Contractor completed 97% of the concrete works and 85% of joint-sealing. The remainig works requires the canal to be shutdown for a period of one week. The Board approve the recommendation of contract termination by the client. pending the finalization of cost escalation request of the contractor. Escallations were paid end of January 2025. | In Progress | 29.88
Reconstruction of canal section between Mahenene Border post and Olushandja Dam: Part B (Olushandja Section) | NamWater | Brumar Construction CC | Namibian | Feb-21 | 631 | Nov-22 | Feb-23 | 51913110.47 | 1412 | 2.24 | 0.99 | Works |  | 11-Sept-24 | The contractor completed concrete works and joint sealing. Overall, the new canal has been put to use since Thursday 10 November 2022. The contractor went back on site end of June 2023 to complete the remaining and for site rehabilitation however work is not yet completed because the remaining work requires the canal to be shutdown for a day or two , contractor waiting on the client for the shutdown of the canal during rainy season. . The Board approve the recommendation of contract termination by the client. pending the finalization of cost escalation request of the contractor. | In Progress | 25.83
NCS/ONB/CPBN-02/2019 (LOT 1 & 2) Provision of Security Guarding Services to NUST | Namibia University of Science and Technology (NUST) | PIS Security Services CC | Namibian | May-21 | 1460 | Apr-24 | Apr-25 | 36715170.96 | 1340 | 0.92 | 0.92 | Non-Consultancy Services | 78 | 21-Jun-23 | The intial contract period lapsed 30 April 2024.The board granted contract extentions as follows; 1. from 01 May 2024- 31 July 2024, 2. from 01 August 2024- 31 October 2024. 3. from 01 November 2024 to 30 April 2025. | In Progress | 35.41
W/ONB/CPBN-01/2020 Northern Railway Extension Phase3 b/w Ondangwa and Oshakati: Construction of Station Buildings and Civil Works | Ministry of Work and Transport | Tatian Trading Enterprises, Ongushe Investment JV | Namibian | May-21 | 916 | May-23 | Nov-23 | 46424178.63 | 1320 | 1 | 1 | Works | 70 | 21-Feb-24 | Project is practically completed by 24 April 2024. The Defects Period commenced on 24 April 2024 and will end 24 April 2025 | In Progress | 45.26
W/OIB/CPBN-03/2020 : Design & Construction of Kunene& Omatando Substations | Nampower | Sinohydro Corporation Limited and Adaptive Building Land Construction CC JV | Namibian JV Chinise | Jun-21 | 692 | Feb-23 | Apr-23 | 340808287 | 1303 | 1 | 1 | Works | 81 | 22-Mar-23 | Project is practically completed and energised on 03 October 2023 for Kunene Substation and and 03 October for Omatando Substation . The Project is in the defects notification period until 22 June 2025 | In Progress | 338.69
W/ONB/CPBN-09/2020: Construction of the Sekelduin Substation | Nampower | Nexus Building Contractor (Pty) Ltd | Namibian | 2021-07-01 | 637 | 2023-01-01 | Mar-23 | 66250272.58 | 1278 | 2.01 | 1 | Works | 85 | 01-Mar-24 | The contractor completed all major construction works by end of March 2023. The defects register items have been completed by end of Nov 2023. The contractor started with remedial work on the demages to the roof ventilator caused by the wind in March 2024. The 24 months defects liablitity period started and will end on 31 March 2025. | In Progress | 60.83
SC/RFP/CPBN-02/2020:Technical Advisory and Project Management Services for the Otjikoto Biomass Power Station | Nampower | 1. Fichter GmbH & Co. KG 2. Lund Consulting Engineers CC 3.Pregon Consulting Engineers (Pty) Ltd | Namibian JV German | 2021-07-01 | 2185 | 2027-06-01 |  | 55728460 | 1274 | 0.58 | 0.58 | Consultancy Services |  |  | The EPC bid closed on 01 December 2023, while the Fuel Supply bid closed on 11 August 2023 and both bids were awarded on 05 April 2024 and contract signed 24 May 2024. Stage 2 commenced by in May 2024 Project Commenced 06 July 2021, average completion is calculated on project timelapsed. | In Progress | 10.57
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Khomas region- LOT 1 | Ministry of Health and Social services | Vicmac Security Services CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 63877248 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 466 | 23-Jun-23 | Contract value not inclusive of the 6 months extentions. Contracts expired end of October 2024 . No request for new procurement recived yet.The contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 83.95
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in //Karas region- LOT 2 | Ministry of Health and Social services | Ombandje Security Services CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 17023392 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 101 | 24-May-24 | Poor service delivery expressed by the client. Guards Lack of supervision, absenteeism of guards and non-patrolling of premises are some of the concerns reported. Salaries are still reported delayed and some times backdated for 3 months due to late submission of invoices with incomplete supporting documents leading to delayed payment of invoices.The contract is extender for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 15.15
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Hardap region- LOT 3 | Ministry of Health and Social services | Windhoek Security Services CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 8154432 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 55 | No site visit conducted | Client is satisfied with the service provisions.The contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 8.58
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Otjozondupa region- LOT 5 | Ministry of Health and Social services | Khaibasen Security Services CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 16404120 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 101 | 20-Sept-24 | Lack of guards supervision is a noted concern by the client and communicated to the service provider for corrective measures. The contract is extender for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 19
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Oshikoto region- LOT 6 | Ministry of Health and Social services | Premiere Investment No.25 | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 16601760 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 152 | 20-Sept-24 | Service provision is going on well, the client expressed satisfaction with the service. Contract value for the 6 months extension period not included hence the expenditures is way ahead. The contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 22.13
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Oshana region- LOT 7 | Ministry of Health and Social services | Omeya Investment CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 10253563.2 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 84 | 26-Jun-23 | Client is satisfied with the service provision. The contract is extender for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 13.74
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Zambezi region- LOT 8 | Ministry of Health and Social services | Independent Security Service CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 18073080 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 110 | 12-Apr-24 | The total cost of the 4 additional quards is yet to be added to the contract value to balance off. The contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 22.15
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Kavango East & West region- LOT 9 | Ministry of Health and Social services | Mukwe Security Service CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 29158224.48 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 129 | 15-Aug-23 | Guards are complaining about delayed salaries, this concern is communicated to the Service provider and promised to address it, monitoring is on-going. The contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 32.7
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Kunene region- LOT 10 | Ministry of Health and Social services | Nelito Investment CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 15331330.08 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 93 | 23-Jun-23 | Service provision is satisfactory as per the client feedback. The contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 14.99
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Omaheke region- LOT 11 | Ministry of Health and Social services | Namibia Protection Services (Pty) Ltd | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 8698707.36 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 88 | No site visit conducted | Contract is extended for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 5.73
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Omusati region- LOT 12 | Ministry of Health and Social services | Triple one Investment CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 20383272 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 190 | 24-Jun-23 | Service provision is going on well, the client expressed satisfaction with the services. The contract is extender for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 23.41
NCS/ONB/CPBN-05/2019: Rendering of Security Services to the Ministry of Health and Social Services in Ohangwena region- LOT 13 | Ministry of Health and Social services | Shikuvule Trading CC | Namibian | 2021-11-01 | 1276 | 2024-10-01 | Apr-25 | 9178401.6 | 1156 | 0.91 | 0.91 | Non-Consultancy Services | 86 | 19-Feb-24 | Service provision is going on well, the client expressed satisfaction with the services and professionalism of the guards. The contract is extender for 6 months from 01 Novemeber 2024 to 30 April 2025. | In Progress | 11.81
W/ONB/CPBN-02/2020: Upgrading, Renovations & Emmergency Repairs to Tubusis Primary School-Phase 1 | Ministry of Education,Arts and Culture | Radial Truss Industries (Pty) Ltd | Namibian | 2022-02-01 | 919 | 2024-08-01 |  | 75229320.2 | 1050 | 1.14 | 0.58 | Works | 56 | 05-Nov-24 | Performance improved with 14 % following the 3 months (April -June) catcp-up submitted by the Contractor to the PA to track progress on the project. progress of work slowed down during the period under review with an everage of 2% per month. The slow down in progress is attributed to the labour unrest and lack of basic building materials on site. The contractor submitted the EOT currently undergoing review by the Client before submission to CPBN for approval | In Progress | 48.59
Tender No. F1/17-5/2011 Support and Maintenance for the Integrated Tax Administration System | Namibia Revenue Agency (NAMRA) | Profile Investment PTY (LTD) JV Beijing CS & S-CA Software Technologies Co. LTD | Namibian JV Chinise | 2022-02-01 | 1095 | 2025-02-01 |  | 49500000 | 1040 | 0.95 | 0.95 | Non-Consultancy Services | 4 |  | Average completion calculated on time lapsed | In Progress | 42.62
W/ONB/CPBN-O72020: Procurement of construction of Otavi Primary School in Otavi, Otjozondjupa Region | Ministry of Education,Arts and Culture | I.D Building Contractors CC | Namibian | 2022-04-01 | 571 | 2023-10-01 |  | 51166019.58 | 999 | 1.75 | 1 | Works | 40 | 16-Nov-23 | The project is practically completed by 26 January 2024. The defect liability period will run until 26 January 2025. | In Progress | 44.41
W/OAB/CPBN-06/2021: Procurement of Upgrading and Extension of Oshikunde Combined School -Phase 2 in Oshikunde, Ohangwena Region | Ministry of Education,Arts and Culture | ETN Technical Services CC | Namibian | Apr-22 | 1090 | 2025-04-01 |  | 68719461.77 | 999 | 0.92 | 0.45 | Works | 68 | 10-Sept-24 | There is a reported continous under-expenditure on the project | Done | 43.48
Procurement Contract for the maintenance service of the electronic border management system | Ministry of Home Affairs and Immigration | Syntex Technologies | Namibian | May-22 | 1096 | 2025-05-01 |  | 48980521.5 | 969 | 0.88 | 0.88 | Non-Consultancy Services |  |  | 2022 - May 2024 | Done | 48
Construction of New Primary | Education,Arts and | I.D Building Contractors CC | Namibian | May-22 | 730 | 2024-05-01 |  | 57597824.03 | 966 | 1.32 | 1 | Works | 26 | 29-Feb-24 | Project is practically completed | Done | 83
Construction of Hostels | Ministry of | NGC Investment CC JV Neu-Olulya | Namibian | May-22 | 1086 | 2025-04-01 |  | 44823933.25 | 966 | 0.89 | 0.02 | Works |  |  | The site has been handed over to the Contractor in June 2022 | Done | 1.121
Provision of Maize meal, | Education,Arts and | Alason Trading Enterprises CC | Namibian | May-22 | 1095 | 2025-05-01 |  | 16522351.18 | 963 | 0.88 | 1 | Goods |  | 21-Aug-23 | Total bags ordered : 104, 918 | Done | 41.4
G/ONB/CPBN-03/2020: Procurement for the Provision of Maize meal, Blending, Packaging and Transportation to Regional Distributors : LOT1, 3, 4 & 12 | Ministry of Education,Arts and Culture | New Success Investments CC | Namibian | Jun-22 | 1095 | 2025-06-01 |  | 48873318.73 | 942 | 0.86 | 0.8 | Goods |  | 16-Aug-23 | Average completion Percentage is calculated on the delivered order | Done | 42.2
G/ONB/CPBN-03/2020:Procurement for the Provision of Maize meal, Blending, Packaging and Transportation to Regional Distributors : LOT 5 & 11 | Ministry of Education,Arts and Culture | Sash Trading and Earthworks CC | Namibian | Jun-22 | 1095 | 2025-06-01 |  | 34868549.52 | 942 | 0.86 | 0.68 | Goods |  | 12-Sept-23 | Average completion Percentage is calculated on the delivered order | Done | 28.3
G/ONB/CPBN-03/2020:Procurement for the Provision of Maize meal, Blending, Packaging and Transportation to Regional Distributors: LOT 7,9 &14 | Ministry of Education,Arts and Culture | Aishaa Investments CC | Namibian | Jun-22 | 1095 | 2025-06-01 |  | 26140749.14 | 942 | 0.86 | 0.54 | Goods |  | 12-Sept-23 | .Average completion Percentage is calculated on the delivered order | Done | 42.2
G/ONB/CPBN-03/2020:Procurement for the Provision of Maize meal, Blending, Packaging and Transportation to Regional Distributors: LOT 8 & 10 | Ministry of Education,Arts and Culture | Kaptau Consumables Supplies CC | Namibian | Jun-22 | 1095 | 2025-06-01 |  | 66921850.86 | 923 | 0.84 | 1.03 | Goods |  | 12-Sept-23 | Average completion Percentage is calculated on the delivered order | Done | 31.6
Construction of Hostels Nationwide: Pendukeni Ivula Ithana Secondary School | Ministry of Education,Arts and Culture | NGC Investment CC JV Neu-Olulya Trading CC | Namibian | Jun-22 | 845 | 2024-10-01 |  | 44823933.25 | 916 | 1.08 | 0.8 | Works | 45 | 11-Sept-24 | The contractor is | Done | 79
NCS/OAB/CPBN-01/2022:Procurement of Vehicle on full Maintenance Lease Basis and Provision of Fleet Management Services to Telecom Namibia for the period of 5 years | Telecom Namibia Ltd | Zeda Namibia (Pty) Ltd T/A Avis Fleet | Namibian | Jul-22 | 1826 | 2027-07-01 |  | 140987210 | 901 | 0.49 | 0.49 | Non-Consultancy Services |  |  | Average completion percentage calculated on the time lapsed, | Done | 48.7
W/OAB/CPBN-03/2022:Operations and Maintenance of the Kupferberg General and Hazardous Waste Disposal Site for Three (3) Years | City of Windhoek (CoW) | Frontier Multi Industries CC | Namibian | Aug-22 | 1092 | 2025-08-01 |  | 38712177.87 | 879 | 0.8 | 0.8 | Works | 113 | No site visit conducted | Average completion calculated on time lapsed | Done | 72
W/OAB/CPBN-01/2021:Procurement of Periodic Maintenance of Gravel Roads: Re-gravelling Contract in the Keetmanshoop Region GRU-KHP-01 | Roads Authority | Adaptive Building and Land Construction CC | Namibian | Aug-22 | 731 | 2024-08-01 | Mar-25 | 126752050.39 | 866 | 1.18 | 0.99 | Works | 43 | 12-Aug-24 | Contractor is 56 days ahead of the program. All road on the list us | Done | 93.86
W/OAB/CPBN-03/2021:Procurement of Periodic Maintenance of Gravel Roads: Re-gravelling Contract in the Oshakati Region GRU-Osh-02 | Roads Authority | Odjove Trading and Construction CC JV Royal Contractors CC | Namibian | Aug-22 | 730 | 2024-08-01 | Jan-25 | 93228108.19 | 866 | 1.19 | 0.6 | Works | 16 | 29-Mar-24 | The Contractor is three weeks behind schedule due to slow | Done | 8.87
Services for UNAM: WHK | Namibia (UNAM) | Rimota Group CC | Namibian | Sept-22 | 1095 | 2025-08-01 |  | 11695744.05 | 852 | 0.78 | 0.78 | Consultancy | 75 | 29-Apr-23 | Contract Signed: 26 Jul- 2022-Work | In Progress | 76
02/2021:Provision of Cleaning | University of | Lizma Trading Enterprises CC | Namibian | Sept-22 | 1095 | 2025-08-01 |  | 5694015.88 | 852 | 0.78 | 0.78 | Consultancy | 30 | 23-Jun-23 | Contract Signed: 26 Jul- 2022-Work | In Progress | 71
NCS/OAB/CPBN-02/2021:Provision of Cleaning Services for UNAM: Oshakati, LOT 3 | University of Namibia (UNAM) | Zayson Trading Enterprises CC | Namibian | Sept-22 | 1095 | 2025-08-01 |  | 2402219.04 | 852 | 0.78 | 0.78 | Non-Consultancy Services | 11 | 16-Sept-23 | cleint satisfied with the service provision | In Progress | 83
NCS/OAB/CPBN-02/2021:Provision of Cleaning Services for UNAM: Ogongo & Ongwediva HP, LOT 4 &9 | University of Namibia (UNAM) | Chippa Trading Enterprises CC | Namibian | Sept-22 | 1095 | 2025-08-01 |  | 4406400 | 852 | 0.78 | 0.53 | Non-Consultancy Services | 25 | 21-Feb-24 | Contract was terminated by the Board at its meeting held on 12 | In Progress | 58
NCS/OAB/CPBN-02/2021:Provision of Cleaning Services for UNAM, Henties Bay & Keetmans, LOT 5 & 6 | University of Namibia (UNAM) | Nova Investments CC | Namibian | Sept-22 | 1095 | Aug-25 |  | 3978482.02 | 852 | 0.78 | 0.78 | Non-Consultancy Services | 21 | 28-Feb-24 |  | In Progress | 3.39
NCS/OAB/CPBN-02/2021:Provision of Cleaning Services for UNAM, Hage Giengob and Jose Eduardo, LOT 8 & 12 | University of Namibia (UNAM) | Lypa Investments CC | Namibian | Sept-22 | 1095 | Aug-25 |  | 7263342.76 | 852 | 0.78 | 0.78 | Non-Consultancy Services | 39 | 26-Mar-23 |  | Done | 4.75
NCS/OAB/CPBN-02/2021:Provision of Cleaning Services for UNAM: Katima & Rundu, LOT 10 & 11 | University of Namibia (UNAM) | Shilimela Construction and CC | Namibian | Sept-22 | 1095 | Aug-25 |  | 10962000 | 852 | 0.78 | 0.78 | Non-Consultancy Services | 29 | 14-Aug-23 |  | Done | 7.71
W/OAB/CPBN-08/2021:Construction of the New Health Centre at Aussenkehr, in the //Karas Region NCS/OAB/CPBN- | Ministry of Health and Social Services | Ongoma Trading Enterprises CC | Namibian | Oct-22 | 670 | Aug-24 |  | 70651945.79 | 818 | 1.22 | 0.8 | Works | 64 | 22-May-24 |  | Done | 61.46
03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 1 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | Nahole Security and Debt Collection Cc | Namibian | Nov-22 | 1095 | Oct-25 |  | 4801032 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 30 | 19-Feb-24 | Contract signed September 2023, works started 01 Novemeber 2022 | Done | 3.4
NCS/OAB/CPBN-03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 2 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | Six Thousand Security Services CC | Namibian | Nov-22 | 1095 | Oct-25 |  | 3856896 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 20 | 24-Mar-23 | Contract signed September 2023, works started 01 Novemeber 2022 | Done | 2.27
NCS/OAB/CPBN-03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 3 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | Chief Nangolo Security Services Cc | Namibian | Nov-22 | 1095 | Oct-25 |  | 5121882 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 32 | No site visit conducted | The Board approved the contact variation of N$ 229,338.00 bringing the contract value to N$ 5, 121,882.00 | Done | 3.1
NCS/OAB/CPBN-03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 4 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | Tripple One Investment Cc | Namibian | Nov-22 | 1095 | Oct-25 |  | 5115000 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 35 | 23-Mar-24 | The Board approved the contact variation of N$ 327,360.00 bringing the contract value to N$ 5, 115,000.00 | Done | 3.1
NCS/OAB/CPBN-03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 5 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | Nelito Investment Cc | Namibian | Nov-22 | 1095 | Oct-25 |  | 5293054 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 45 | 22-Mar-24 | Contract signed September 2023, works started 01 Novemeber 2022 | Done | 3.74
NCS/OAB/CPBN-03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 6 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | PIS Security Servicess Cc | Namibian | Nov-22 | 1095 | Oct-25 |  | 3047003 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 19 | 29-Mar-23 | The Board approved the contact variation of N$ 304,742.00 bringing the contract value to N$ 3,047,003.00 | Done | 2.14
NCS/OAB/CPBN-03/2022:Procurement of the provision of security services to the ministry of gender equality,Poverty eradication and social welfare-LOT 7 | Ministry of Gender Equality,Poverty Eradication and Social Welfare | Sirka Investment Cc | Namibian | Nov-22 | 1095 | Oct-25 |  | 3883680 | 791 | 0.72 | 0.72 | Non-Consultancy Services | 26 | 24-May-24 | The Board approved the PE to do direct procurement to Sirka Investment CC for additional guards to be attached to new offices and sites that were omitted at bidding stageto the value of N$ 1,941,840.00 bringing the contract value to N$ 3,883,680.00 | Done | 3.97
W/RB/CPBN-01/2022: Completion of the remaining Works at Nkurenkuru VTC | NamibiaTraining Authority | Betonsein Construction CC | Namibian | Nov-22 | 599 | Jul-24 |  | 30625566.49 | 782 | 1.31 | 1 | Works | 32 | 29-Aug-24 | Expenditure report as at 31 July 2024 | Done | 14.08
NCS/OAB/CPBN-02/2022-Rendering of Security Services and Cash -in-transit to NamWater for a period of 36 Months-LOT 1 &LOT4 | NamWater | EASS Investment | Namibian | Jan-23 | 1095 | Dec-25 |  | 7305336 | 730 | 0.67 | 0.67 | Non-Consultancy Services | 26 | No site visit conducted | Contract signed 08 November 2022. Contract value revised from N$ 8,348,572.80 to N$ 7,305,336.00 | Done | 1.83
NCS/OAB/CPBN-02/2022-Rendering of Security Services and Cash -in-transit to NamWater for a period of 36 Months-LOT 2 &LOT 3 | NamWater | PIS Security Services | Namibian | Jan-23 | 1095 | Dec-25 |  | 19914334.79 | 730 | 0.67 | 0.67 | Non-Consultancy Services | 125 | No site visit conducted | Contract signed 04 November 2022.Contract value revised from N$ 18,895,680.00 to N$ 19,914,334.79 | Done | 4.44
W/OAB/CPBN-02/2021-Periodic Maintenance of Roads: Re-Gravelling Contract in the Otjiwarongo Region-GRU-OTJ2: LOT 2 | Roads Authority | John Namusheshe Construction & Investment CC | Namibian | Jan-23 | 730 | Jan-25 |  | 85217412.21 | 708 | 0.97 | 0.23 | Works | 15 | 27-Jul-24 | Work is behind schedule due to delayed site handover, attributed to the Builder's holiday.Progress as at Dec 2023, | In Progress | 19.81
W/OAB/CPBN-02/2021-Periodic Maintenance of Roads: Re-Gravelling Contract in the Otjiwarongo Region-GRU-OTJ1: LOT 1 | Roads Authority | Octagon Construction (Pty) Ltd | Namibian | Feb-23 | 731 | Feb-25 |  | 89909534.96 | 698 | 0.95 | 0.1 | Works | 19 | 26-Jul-24 | Work is behind schedule with 428 Production days. Due to lack of capacity by the Contractor | In Progress | 8.9
Provision of Security Services to the Kavango West Region for a period of thirty-six (36) months | Kavango West Regional Council | Onyeka Protection Services CC | Namibian | Mar-23 | 1096 | Feb-26 |  | 10077926.4 | 671 | 0.61 | 0.61 | Non-Consultancy Services | 97 | 30-Aug-24 | Contract Signed on 16 January 2023, work commenced on 01 March 2023 | In Progress | 6.67
W/OAB/CPBN-04/2021:Procurement for Construction of a New Primary School at Mix Settlement, Brakwater | Ministry of Education,Arts and Culture | James and Young Trading Enterprise CC | Namibian | Mar-23 | 636 | Nov-24 |  | 56647200.13 | 670 | 1.05 | 0.37 | Works | 12 | 29-Jun-24 | Contract Signed: 07 Jul- 2022: Site handover was done on 9 December 2022, and work commerced in March 2023. The project is delayed by the absence of drawings from the structural Engineer. CPBN wrote to mInistry of education to delibarate on the way forward and yet to recieve a response. | In Progress | 18.33
W/OAB/CPBN-01/2022-Development Contract for the Blading of Gravel Roads in the Windhoek Region-DC-WHK 02 | Roads Authority | Earth Ethicks Construction CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 75774420 | 640 | 0.35 | 0.3 | Works |  | No site visit conducted |  | In Progress | 22.46
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | NDES Civil Works Construction CC and NDES Trading Enterprises CC JV | Namibian | Apr-23 | 1826 | Mar-28 |  | 14000539.36 | 640 | 0.35 | 0.25 | Works |  | No site visit conducted |  | Done | 3.5
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | J. O Opitome Trading CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 14376426 | 640 | 0.35 | 0.33 | Works |  | No site visit conducted |  | Done | 4.73
W/OAB/CPBN-01/2022-Development Contract for the Blading of Gravel Roads in the Windhoek Region-DC-WHK 04 | Roads Authority | Globex investment CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 76965733.75 | 640 | 0.35 | 0.27 | Works |  | 02-Aug-24 |  | Done | 21.04
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Omuve Construction Technologies CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 14708488.5 | 640 | 0.35 | 0.29 | Works |  | No site visit conducted |  | Done | 4.23
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Sumseno Contracting CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 14234504.5 | 640 | 0.35 | 0.28 | Works |  | No site visit conducted |  | Done | 4.01
W/OAB/CPBN-01/2022-Development Contract for the Blading of Gravel Roads in the Windhoek Region-DC-WHK 06 | Roads Authority | John Namusheshe Construction & Investment CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 51548750 | 640 | 0.35 | 0.23 | Works |  | 01-Aug-24 |  | Done | 11.93
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Illimite Investment CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 14660976.25 | 640 | 0.35 | 0.25 | Works |  | 01-Aug-24 |  | In Progress | 3.71
W/OAB/CPBN-01/2022-Development Contract for the Blading of Gravel Roads in the Windhoek Region-DC-WHK 07 | Roads Authority | John Namusheshe Construction & Investment CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 95736120 | 640 | 0.35 | 0.12 | Works |  | 27-Jul-24 | Contract was terminated by the Board at its meeting held on 03 October 2024 due to non-performance | In Progress | 15.69
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Kunene River Construction and Electrical CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 14685274.3 | 640 | 0.35 | 0.3 | Works |  | No site visit conducted |  | In Progress | 4.5
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Kai Engineering and Fabrication CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 16267900 | 640 | 0.35 | 0.28 | Works |  | No site visit conducted |  | In Progress | 4.67
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Fillemon Investments and Trucks CC | Namibian | Apr-23 | 1826 | Mar-28 |  | 15571954.5 | 640 | 0.35 | 0.09 | Works |  | 12-Jul-24 | Contract was terminated by the Board at its meeting held on 29 August 2024 due to non-performance | In Progress | 1.7
W/OAB/CPBN-01/2022: Development Contracts for the Blading of Gravel Roads in Windhoek Region | Roads Authority | Earth Ethicks Construction CC | Namibian | Apr-23 | 1856 | Apr-28 |  | 58226892 | 640 | 0.34 | 0.22 | Works |  | No Site visit conducted |  | In Progress | 12.84
Nominated SME-subcontractors for the Blading and Gravel Roads in the Windhoek Region | Roads Authority | Shiveli Trading Enterprises CC | Namibian | Apr-23 | 1826 | Mar-28 | Oct-24 | 15760267 | 640 | 0.35 | 0.29 | Works |  | No site visit conducted | No report received from PE for the reporting period | In Progress | 4.03
Provision of Landscaping and Gardening Services (UNAM): Oshakati Campus | University of Namibia (UNAM) | Bertlynne Investment CC | Namibian | May-23 | 1095 | Apr-26 |  | 3586664.01 | 610 | 0.56 | 0.56 | Non-Consultancy Services | 17 | No site visit conducted | Contract Signed on 24 January 2023, Contract comencened 01 May 2023 | In Progress | 1.81
Provision of Landscaping and Gardening Services (UNAM): Katima Campus | University of Namibia (UNAM) | Ba Sharon | Namibian | May-23 | 1096 | Apr-26 |  | 2120280 | 610 | 0.56 | 0.56 | Non-Consultancy Services | 11 | 28-Nov-23 | Contract Signed on 27 January 2023, Works commenced 01 May 2023 | In Progress | 107
Provision of Landscaping and Gardening Services (UNAM): Khomasdal Campus | University of Namibia (UNAM) | Namibia Landscapes CC | Namibian | May-23 | 1096 | Apr-26 |  | 2377520 | 610 | 0.56 | 0.56 | Non-Consultancy Services | 12 | No site visit conducted | Contract Signed on 20 January 2023, Works commenced 01 May 2023 | In Progress | 1.23
Provision of Landscaping and Gardening Services (UNAM): Sam Nujoma Campus | University of Namibia (UNAM) | Roots Nursery & Garden Centre CC | Namibian | May-23 | 1096 | Apr-26 |  | 1331213.88 | 610 | 0.56 | 0.56 | Non-Consultancy Services | 6 | No site visit conducted | Contract Signed on 20 January 2023, Works commenced 01 May 2023 | In Progress | 0.65
Rendering of Security Services and Cash -in-transit to Telecom for a period of 36 Months-LOT 2 | Telecom Namibia Ltd | Omeya Investment CC | Namibian | May-23 | 1096 | May-26 |  | 4251789 | 594 | 0.54 | 0.54 | Non-Consultancy Services | 25 | No site visit conducted | Average completion is calculated on time lapsed | In Progress | 1.8